## Question 1
Activity | Predecessor | Optimal | Normal | Pessimistic | Expected Task Duration
a |  | 4 | 6 | 8 | 6
b |  | 3 | 5 | 9 | 5.3333
c | a | 4 | 5 | 7 | 5.1667
d | a | 5 | 7 | 10 | 7.1667
e | b,c | 3 | 5 | 8 | 5.1667
f | d | 2 | 4 | 7 | 4.1667
g | e | 3 | 5 | 8 | 5.1667
h | a,b | 4 | 8 | 10 | 7.6667
i | h,g | 2 | 3 | 5 | 3.1667
j | d,e,f | 4 | 5 | 9 | 5.5
#end | i,j | 0 | 0 | 0 | 0

## Question 2
Project Duration
Activity | Description | Immediate Predecessor(s) | Expected Duration | ES | EF | LS | LF | Slack
a | Start Of Project |  | 6 | 0 | 6 | 0 | 6 | 0
b |  |  | 5.3333 | 0 | 5.3333 | 5.8333 | 11.1667 | 5.8333
c |  | a | 5.1667 | 6 | 11.1667 | 6 | 11.1667 | 0
d |  | a | 7.1667 | 6 | 13.1667 | 7.8333 | 15 | 1.8333
e |  | b,c | 5.1667 | 11.1667 | 16.3333 | 11.1667 | 16.3333 | 0
f |  | d | 4.1667 | 13.1667 | 17.3333 | 15 | 19.1667 | 1.8333
g |  | e | 5.1667 | 16.3333 | 21.5 | 16.3333 | 21.5 | 0
h |  | a,b | 7.6667 | 6 | 13.6667 | 13.8333 | 21.5 | 7.8333
i |  | h,g | 3.1667 | 21.5 | 24.6667 | 21.5 | 24.6667 | 0
j |  | d,e,f | 5.5 | 17.3333 | 22.8333 | 19.1667 | 24.6667 | 1.8333
#end |  | i,j | 0 | 24.6667 | 24.6667 | 24.6667 | 24.6667 | 0
|  |  |  | Minimum Project Length | 24.6667
Enter Task list and precedences below, with estimated durations for each task
The calculation mode is set to MANUAL, so to perform a single PERT iteration, click "Recalculate Sheet" in the "Formulas" tab
Note on A7: Bob York: Note: there is an implementation issue here that concerns the Activity labels. Since the formulae make use of the FIND() function, any Activity label that can be "found" inside aother activity label will create a problem. For example, if one activity is labeled "START" and another activity is labeled "A", this creates a problems since "A" can be found within the label "START". As per Ragsdale's paper ("A New Approach to Implementing Project Networks in Spreadsheets"), this could be avoided by using double-digit task labels like 01,02,03,,,,,99, provided that columns "A" and "C" are formatted as TEXT. If there are more than 100 tasks, then using three digits (001, 002,003,.....999) would then be the preferred approach.
Note on E7: Bob York: Note that this column is an array formula. In the Mac 2011 version of Excel, the only way to enter these correctly is by first entering the formula in the first row, the selecting "command-return" to indicate that it is an array formula, then selecting the cell and dragging it downwards through the appropriate rows. According to Ragsdale's paper, in the PC version of Excel the procedure is reversed: the formula is entered in the top row, dragged downward through the desired rows, and then the array formula is indicated by a CTRL-SHIFT-ENTER operation. Attempting it this way in Mac 2011 does not increment some of the cell references correctly
Note on H7: Bob York: See comment in G7